## Sprint Tasks
Task ID | Task Name | Hours | Sprint | Story | Dependencies
TASK-001 | Design password reset email template | 4 | Sprint 1 | STORY-201
TASK-002 | Implement token generation service | 12 | Sprint 1 | STORY-201
TASK-003 | Create password reset API endpoint | 8 | Sprint 1 | STORY-201 | TASK-002
TASK-004 | Build password reset UI | 8 | Sprint 2 | STORY-201 | TASK-003
TASK-005 | Implement MFA TOTP generation | 16 | Sprint 1 | STORY-202
TASK-006 | Create MFA setup wizard | 12 | Sprint 2 | STORY-202 | TASK-005
TASK-007 | Build MFA verification flow | 8 | Sprint 2 | STORY-202 | TASK-005
TASK-008 | Create session management dashboard | 16 | Sprint 2 | STORY-203
TASK-009 | Implement session termination API | 8 | Sprint 3 | STORY-203
TASK-010 | Add session activity logging | 8 | Sprint 3 | STORY-203 | TASK-009

## Capacity
Sprint | Total Hours
Sprint 1 | 50
Sprint 2 | 55
Sprint 3 | 45